## Sheet1
Task | Start | End | Duration | %Done | Notes
Research | 2025-10-07 | 2025-10-21 | 15 | 0% | Read about Zakat rules, AI use cases, and islamic finance principles
Requirements & Personas | 2025-10-21 | 2025-11-04 | 15 | 0% | Interview sample users; define personas (single, married, etc.)
Design & Planning | 2025-11-04 | 2025-11-18 | 15 | 0% | Create wireframes and database
Backend Setup & Auth | 2025-11-18 | 2025-12-02 | 15 | 0% | Set up Flask app and user login system
ML Model Developement | 2025-12-02 | 2025-12-16 | 15 | 0% | Train zakat prediction model using sample income data
AI Forecasting & Intelligence | 2025-12-16 | 2025-12-30 | 15 | 0% | Develop model to forecast income and savings
UI Development | 2025-12-30 | 2026-01-06 | 8 | 0% | Build dashboard and input forms
Testing & Security Evaluation | 2026-02-06 | 2026-03-02 | 25 | 0% | Run unit tests and check for vulnerabilities
Report Writing and Presentation | 2026-02-20 | 2026-04-01 | 41 | 0% | Draft report and prepare presentation slides
Final Submission & Polish | 2026-04-01 | 2026-04-15 | 15 | 0% | Final review before submitting